## Progress Planning and Tracking
Project Name: | PBI - Sales
Report Date: | 2026-01-23
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12
Planning | Define requirements and tools | 100% | Completed | Mallory, Mavis | 2026-01-25: 2; 2026-02-01: 8; 2026-02-08: 10
| Source database from Kaggle | 100% | Completed | Mallory, Mavis | 2026-01-25: 2; 2026-02-01: 1
| Rough draft dashboard layout | 100% | Completed | Mavis | bar: 2026-02-01
Project design | Cleanse Data in database with | 100% | Completed | Mallory | 2026-02-08: 2; 2026-02-15: 1
Power Query | bar: 2026-02-08 to 2026-02-15
| Create Data models with database | 100% | Completed | Mallory | 2026-02-15: 1; 2026-02-22: 6; 2026-03-01: 2; 2026-03-15: 2; 2026-03-22: 2
| Create Visual models | 100% | Completed | Mallory | 2026-03-01: 5; 2026-03-08: 4; 2026-03-15: 1; 2026-03-22: 2
| Finalize layout with visual models | 100% | Completed | Mavis | 2026-03-08: 4
| Test prototype | 100% | Completed | Mallory | 2026-03-15: 1; 2026-03-22: 2
Development | Review prototype design | 100% | Completed | Mallory | 2026-03-08: 2; 2026-03-15: 4; 2026-03-22: 2
| Rework requirements | 100% | Completed | Mavis | 2026-03-01: 4; 2026-03-08: 4; 2026-03-15: 4
| Document updated design | 100% | Completed | Mavis | 2026-03-01: 4; 2026-03-08: 4; 2026-03-15: 4; 2026-03-22: 8; 2026-03-29: 8
| Test product | 100% | Completed | Mavis | 2026-03-29: 4; 2026-04-05: 6
Final report | Presentation preparation | 100% | Completed | Mallory, Mavis | 2026-03-22: 4
| Final Package | 100% | Completed | Mallory | 2026-03-29: 26; 2026-04-05: 12; 2026-04-12: 8
| Final report submission to D2L and project owner | 100% | Completed | Mallory | 2026-04-05: 1; 2026-04-12: 2
|  |  | Total work hours | 170 | 4 | 10 | 12 | 2 | 6 | 15 | 18 | 16 | 20 | 38 | 19 | 10
* formally define how you will develop this project including source code management
Legend
Planned
Delayed
Number | Work: man hours